## Slide 1: Lecture 19 & 20
Using a Weighted Scoring Model
Implementing a Balanced Scorecard
Developing a Project Charter
Developing a Project Management Plan
Project Management Plan Contents
Using Guidelines to Create Project Management Plans
Directing and Managing Project Work
Coordinating Planning and Execution
Providing Strong Leadership and a Supportive Culture
Capitalizing on Product
Business, and Application Area Knowledge
Project Execution Tools and Techniques
Monitoring and Controlling Project Work
Performing Integrated Change Control
Change Control on IT Projects, Change Control System,
Closing Projects or Phases
Using Software to Assist in Project Integration Management
Chapter Summary
Reading material:
Sch-chap pg. 153- 175

## Slide 2: Weighted Scoring Model
A weighted scoring model is a tool that provides a systematic process for selecting projects based on many criteria
    Identify criteria important to the project selection process
    Assign weights (percentages) to each criterion so they add up to 100%
    Assign scores to each criterion for each project
    Multiply the scores by the weights and get the total weighted scores
The higher the weighted score, the better

## Slide 3: Sample Weighted Scoring Model for Project Selection

## Slide 4: Implementing a Balanced Scorecard
Drs. Robert Kaplan and David Norton developed this approach to help select and manage projects that align with business strategy
A balanced scorecard:
  Is a methodology that converts an organization’s value drivers, such as customer service, innovation, operational efficiency, and financial performance, to a series of defined metrics

## Slide 5: Balanced Scorecard Example

## Slide 6: Analytic Hierarchy Process (AHP)
AHP is a Multicriteria Decision-Making Theory (MCDM) that allows one to simultaneously consider both qualitative and quantitative factors to rank-order alternatives.

## Slide 7: Project Charters
After deciding what project to work on, it is important to let the rest of the organization know
A project charter is a document that formally recognizes the existence of a project and provides direction on the project’s objectives and management
Key project stakeholders should sign a project charter to acknowledge agreement on the need and intent of the project; a signed charter is a key output of project integration management

## Slide 8: Project Charter for the DNA-Sequencing Instrument Completion Project

## Slide 10: Project Management Plans
A project management plan is a document used to coordinate all project planning documents and help guide a project’s execution and control
Plans created in the other knowledge areas are subsidiary parts of the overall project management plan

## Slide 11: Common Elements of a Project Management Plan
Introduction or overview of the project
Description of how the project is organized
Management and technical processes used on the project
Work to be done, schedule, and budget information

## Slide 12: Sample Contents for a Software Project Management Plan (SPMP)

## Slide 13: Project Execution
Project execution involves managing and performing the work described in the project management plan
The majority of time and money is usually spent on execution
The application area of the project directly affects project execution because the products of the project are produced during execution

## Slide 14: Coordinating Planning and Execution
Project planning and execution are intertwined and inseparable activities
Those who will do the work should help to plan the work
Project managers must solicit input from the team to develop realistic plans

## Slide 15: Providing Leadership and a Supportive Culture
Project managers must lead by example to demonstrate the importance of creating and then following good project plans
Organizational culture can help project execution by:
  Providing guidelines and templates
  Tracking performance based on plans
Project managers may still need to break the rules to meet project goals, and senior managers must support those actions

## Slide 16: Important Skills for Project Execution
General management skills like leadership, communication, and political skills
Product, business, and application area skills and knowledge
Use of specialized tools and techniques

## Slide 17: Project Execution Tools and Techniques
Expert judgment: experts can help project managers and their teams make many decisions related to project execution
Project management information systems: there are hundreds of project management software products available on the market today, and many organizations are moving toward powerful enterprise project management systems that are accessible via the Internet

## Slide 18: Monitoring and Controlling Project Work
Changes are inevitable on most projects, so it’s important to develop and follow a process to monitor and control changes
Monitoring project work includes collecting, measuring, and disseminating performance information
A baseline is the approved project management plan plus approved changes

## Slide 19: Integrated Change Control
Three main objectives are:
  Influencing the factors that create changes to ensure that changes are beneficial
  Determining that a change has occurred
  Managing actual changes as they occur

## Slide 20: Change Control on Information Technology Projects
Former view: the project team should strive to do exactly what was planned on time and within budget
Problem: stakeholders rarely agreed up-front on the project scope, and time and cost estimates were inaccurate
Modern view: project management is a process of constant communication and negotiation
Solution: changes are often beneficial, and the project team should plan for them

## Slide 21: Change Control System
A formal, documented process that describes when and how official project documents and work may be changed
Describes who is authorized to make changes and how to make them

## Slide 22: Change Control Board (CCB)
A formal group of people responsible for approving or rejecting changes on a project
CCBs provide guidelines for preparing change requests, evaluate change requests, and manage the implementation of approved changes
Includes stakeholders from the entire organization

## Slide 23: Making Timely Changes
Some CCBs only meet occasionally, so it may take too long for changes to occur
Some organizations have policies in place for time-sensitive changes
  “48-hour policy” allows project team members to make decisions; then they have 48 hours to reverse the decision pending senior management approval
  Delegate changes to the lowest level possible, but keep everyone informed of changes

## Slide 24: Configuration Management
Ensures that the descriptions of the project’s products are correct and complete
Involves identifying and controlling the functional and physical design characteristics of products and their support documentation
Configuration management specialists identify and document configuration requirements, control changes, record and report changes, and audit the products to verify conformance to requirements

## Slide 25: Suggestions for Performing Integrated Change Control

## Slide 26: Closing Projects and Phases
To close a project or phase, you must finalize all activities and transfer the completed or cancelled work to the appropriate people
Main outputs include:
  Final product, service, or result transition
  Organizational process asset updates

## Slide 27: Using Software to Assist in Project Integration Management
Several types of software can be used to assist in project integration management
  Documents can be created with word processing software
  Presentations are created with presentation software
  Tracking can be done with spreadsheets or databases
  Communication software like e-mail and Web authoring tools facilitate communications
  Project management software can pull everything together and show detailed and summarized information
  Business Service Management (BSM) tools track the execution of business process flows

## Slide 28: Chapter Summary
Project integration management involves coordinating all of the other knowledge areas throughout a project’s life cycle
Main processes include:
  Develop project charter
  Develop project management plan
  Direct and manage project execution
  Monitor and control project work
  Perform integrated change control
  Close the project or phase