## Slide 1
PERT - The Program Evaluation and Review Technique
Methods and techniques of MBP

## Slide 2
PERT
The Program Evaluation and Review Technique (PERT)
a technique (mean) that analyzes all tasks involved in completing a given project,
especially to analyze the time needed to complete each task, and identifying the minimum time needed to complete the total project (the critical path).
PERT was developed in the 1950’s, primarily to simplify the planning and scheduling of large and complex projects.
Definition:
http://en.wikipedia.org

## Slide 3
PERT
An arrow-node diagram – a task network for a project made with arrows and small circles.
Definition:
http://en.wikipedia.org
A precedence diagram – a task network for a project made with boxes and realtionship lines.

## Slide 4
PERT
Nomenclature (key terms):
The event number
The earliest possible start time of the event
The slack time
The latest possible finish time of the event
event - end point that represents the completion of major activity

## Slide 5
PERT
Nomenclature (key terms):
Activity – time required to progress from one event to another
Links – neither time nor activity relationship
Critical Activity – activity with zero slack time

## Slide 6
PERT
events - end points that represent the completion of major activities
activities - time or resources required to progress from one event to another
slack time - amount of time an activity can be delayed without delaying the entire project
critical path - the most time-consuming sequence of events and activities in a PERT network
delays on critical path will delay completion of the entire project (zero slack time)
Nomenclature (key terms):
© Prentice Hall, 2002
0
0
0
0
2
3
5
4

## Slide 7
PERT
Nomenclature (key terms):
milestone – a strategic event that end certain group of activities
14
0
14
8
14
0
14
7
14
0
14
6
14
0
14
5
14
0
14
4
14
0
14
9
14
0
14
10

## Slide 8
PERT - methodology
Step 1: Create a table – activity / duration
Step 2: Name events accordingly to the table
Step 3: Link all the events with planned activities
Step 4: Add duration time for each activity
Step 5: Enter The earliest possible start time for every event
Step 6: Enter the latest possible finish time for every event
Step 7: Evaluate the slack time for every event
Step 8: Underline (in red) the critical path of the entire project
Step 9: Select milestones for the project
Procedure „step-by-step”:

## Slide 9
PERT - methodology
Activity: Duration:
Activity a 2
Activity b 4
Activity c 4
Activity d 3
Activity e 5
Activity f 3
Activity g 2
Activity h 4
Activity i 2
Activity j 3
Step 1: Create a table – activity / duration

## Slide 10
PERT - methodology
Step 2: name events accordingly to the table
0
2
4
8
9
10
1
5
3
7
6

## Slide 11
PERT - methodology
Step 3: Link all the events with planned activities
0
2
4
8
9
10
1
5
3
7
6
a
b
c
d
e
f
g
h
i
j
k
l

## Slide 12
PERT - methodology
Step 4: Add duration time for each activity
0
2
4
8
9
10
1
5
3
7
6
2
4
4
3
5
3
6
2
4
2
2
3
a
b
c
d
e
f
g
h
i
j
k
l

## Slide 13
PERT - methodology
Step 5: Enter The earliest possible start time for every event
0
0
4
2
7
4
14
8
16
9
19
10
2
1
7
5
8
3
10
7
10
6
2
4
4
3
5
3
6
2
4
2
2
3
a
b
c
d
e
f
g
h
i
j
k
l

## Slide 14
PERT - methodology
Step 6: Enter the latest possible finish time for every event
0
0
0
4
4
2
7
12
4
14
14
8
16
16
9
19
19
10
2
5
1
7
10
5
8
8
3
10
10
7
10
13
6
2
4
4
3
5
3
6
2
4
2
2
3
a
b
c
d
e
f
g
h
i
j
k
l

## Slide 15
PERT - methodology
Step 7: Evaluate the slack time for every event
0
0
0
0
4
0
4
2
7
5
12
4
14
0
14
8
16
0
16
9
19
0
19
10
2
3
5
1
7
3
10
5
8
0
8
3
10
0
10
7
10
3
13
6
2
4
4
3
5
3
6
2
4
2
2
3
a
b
c
d
e
f
g
h
i
j
k
l

## Slide 16
PERT - methodology
Step 8: Underline (in red) the critical path of the entire project
0
0
0
0
4
0
4
2
7
5
12
4
14
0
14
8
16
0
16
9
19
0
19
10
2
3
5
1
7
3
10
5
8
0
8
3
10
0
10
7
10
3
13
6
2
4
4
3
5
3
6
2
4
2
2
3
a
b
c
d
e
f
g
h
i
j
k
l

## Slide 17
PERT - methodology
Step 9: Select milestones for the project
0
0
0
0
4
0
4
2
7
5
12
4
14
0
14
8
16
0
16
9
19
0
19
10
2
3
5
1
7
3
10
5
8
0
8
3
10
0
10
7
10
3
13
6
2
4
4
3
5
3
6
2
4
2
2
3
a
b
c
d
e
f
g
h
i
j
k
l